## Intro
Our Solution
Smart
Co

## Tasks
|  |  | CUBE: | smartco:Task Workflow
|  |  | organization | Massachusetts | 2015
FY2015 Budget Application Instructions
| Days Left | Overdue |  | Task | Launch | Status | Due Date | Commentary
All Tasks | 0 |  |  | All Tasks |  | In Progress
1 | 0 |  |  | Revenue |  | In Progress
2 | -581 |  |  | Enter New Products |  | Complete | 2013-08-08 | Price increase in 4G product line to boost Margin
3 | -581 | Overdue |  | Plan Units Sold |  | Not Started | 2013-08-08
5 | 0 |  |  | Headcount |  | Complete
7 | -452 |  |  | Amend Existing / Add new Headcount |  | Complete | 2013-12-15
8 | -452 |  |  | Review Total Compensation Spend |  | Complete | 2013-12-15
9 | 0 |  |  | Capital |  | Not Started
10 | -452 | Overdue |  | Add New Capital Requests |  | Not Started | 2013-12-15
11 | -452 | Overdue |  | Review IS and BS Impact |  | Not Started | 2013-12-15
12 | 0 |  |  | OPEX |  | Complete
13 | -452 |  |  | Plan Marketing expense |  | Complete | 2013-12-15
14 | -452 |  |  | Plan Phased costs |  | Complete | 2013-12-15
15 | 0 |  |  | Income Statement |  | In Progress
16 | -452 |  |  | Review Allocations |  | Complete | 2013-12-15
17 | -452 | Overdue |  | Update Forecast |  | Not Started | 2013-12-15
18 | -452 | Overdue |  | Review Exchange Differences |  | Not Started | 2013-12-15
19 | -452 |  |  | Review Final P&L |  | Complete | 2013-12-15
Budget Application Instructions

## Status
Task Status |  | Metrics Status
smartco:Task Workflow |  |  | smartCo:incomeStatement | smartCo:incomeStatement | smartCo:incomeStatement
Massachusetts |  |  | Local | Local | Local
|  |  | y2 | y2 | y2
|  |  | 2015 | 2015 | 2015
|  |  | Year | Year | Year
|  |  | Target | Budget | Variance
7 | 5 |  | Target 2015 | Budget 2015 | Variance
|  | Gross Margin | 1737619.9841 | 1929763.1203 | 192143.1362 | 0
Tasks Completed | Tasks Remaining | 6099 PAYROLL | 1097896.1068 | 669755.3934 | 428140.7134 | 0
|  | 6499 MARKETING | 145183.412 | 137984.92 | 7198.492 | 0
|  | 6599 DEPRECIATION | 84068.0167 | 85000 | -931.9833 | 1
|  | Net Profit | -17093.2906 | 604800.0469 | 621893.3375 | 0
|  | # Incomplete Metrics | 1
Tasks Completed | 7
Tasks Remaining | 5
Plan Progress

## {PL}PickLst (hidden)
Complete
Not Started